## Timeline
Date by Half Week (Sept - Dec 2015)
Type | Description | 2015-09-28 | 2015-10-01 | 2015-10-05 | 2015-10-08 | 2015-10-12 | 2015-10-15 | 2015-10-19 | 2015-10-22 | 2015-10-26 | 2015-10-29 | 2015-11-02 | 2015-11-05 | 2015-11-09 | 2015-11-12 | 2015-11-16 | 2015-11-19 | 2015-11-23 | 2015-11-26 | 2015-11-30 | 2015-12-03 | 2015-12-07 | 2015-12-09
Non-Technical | Requirements Understood | bar: 2015-09-28
Development of System Design | bar: 2015-09-28 to 2015-10-05
Allocation of Tasks | bar: 2015-10-05
Submission 3 Requirements Questions | bar: 2015-10-01
Submission of 2 Systems Questions | bar: 2015-10-15
Class Diagrams | bar: 2015-10-05 to 2015-10-08; 2015-10-19; 2015-11-12 to 2015-11-16; 2015-12-03
Case Diagrams | bar: 2015-10-05 to 2015-10-08; 2015-10-19; 2015-11-12 to 2015-11-16; 2015-12-03
Design v1 Accomplished | bar: 2015-10-22
Submission of Stage 1 | bar: 2015-10-26
Design v2 Accomplished | bar: 2015-11-23
Submission of Stage 2 | bar: 2015-11-26
Inspection and OO Metrics | bar: 2015-11-30
Final Report | bar: 2015-12-03
Design v3 Accomplished | bar: 2015-12-07
Submission of Stage 3 | bar: 2015-12-09
Back End Functionality | File Selection/Location | bar: 2015-10-12 to 2015-10-19
File Reading | bar: 2015-10-12
Row Objects | bar: 2015-10-08
Row Builder (Grant Only) | bar: 2015-10-12 to 2015-10-15
Attribute Builder | bar: 2015-10-12 to 2015-10-15
Error Checking (Grant Only) | bar: 2015-10-19
Director Class | bar: 2015-10-08 to 2015-10-22
Construction of Map (Grant Only) | bar: 2015-10-19
Objects for "+/-" List Display (a) | bar: 2015-10-08
Objects for Graph Display (b) | bar: 2015-10-12
Builder for (a) (Grant Only) | bar: 2015-10-15
Builder for (b) (Grant Only) | bar: 2015-10-15
Remaining Builders for (a) | bar: 2015-10-29 to 2015-11-05
Remaining Builders for (b) | bar: 2015-10-29 to 2015-11-05
Remaining Row Builders | bar: 2015-10-29 to 2015-11-02
Remaining Error Checking (other file type) | bar: 2015-11-02 to 2015-11-05
Remaining Map Construction (other file type) | bar: 2015-11-02 to 2015-11-05
Front End Functionality | Modification Based on Feedback from v1 | bar: 2015-11-09 to 2015-11-16
Modification Based on Feedback from v2 | bar: 2015-11-30 to 2015-12-03
File Selection/Location | bar: 2015-10-12 to 2015-10-15
Main Window | bar: 2015-10-08 to 2015-10-19
"+/-" Display List/Tree | bar: 2015-10-12
Bar Graph | bar: 2015-10-12 to 2015-10-19
Pie Graph | bar: 2015-10-12 to 2015-10-19
Graph Printing | bar: 2015-10-19
Date Range Selection | bar: 2015-10-19
Name Entry | bar: 2015-10-19
Green - Completed
Blue - Planned

## AgentTask
Assigned To:
Task | Description | Colin Costello | Eric Lefebvre | James Crocker | Junwon Seo | Kevin Tawaststjerna | Lankesh Patel | Larsen Burchall | Peter Pfoertsch | Song Gao | Yiming Guan
System Design | Decisions on classes, interfaces between classes etc. This refers to the overall design of our program.
Class Diagrams | Diagrams of classes to be used in the program. Related to the above task.
Case Diagrams | Required for v1 and v2 submissions.
Sequence Diagram | Required for v2 submission.
Package Diagram | Required for v2 submission.
Design Pattern Description | Required for v2 submission.
C++ Implementation Justification | Required for v2 submission.
File Selection/Location | Both the GUI and programming work that relates to prompting a user for the type of file, asking for the file name and locating the file.
Row Objects | Objects to contain the necessary data to be pulled from rows in the excel file. One for each file type.
Row Builder (Grant Only) | This builder is responsible for taking a given Grant row, and using the attribute builder to create a Grant row object.
Attribute Builder | This builder will take a row and location, returning either a name, date, or primitive type like a string or int.
Error Checking (Grant Only) | Determine if a particular row contained incorrect data.
Director Class | This is the class that oversees map creation, row building, error checking etc. The rows of the file will be read here.
Object for +/- List | This is a simplified object to be passed to the +/- List GUI for display.
Object for Graphs | This is a simplified object to be passed to a Bar or Pie Graph for display.
Builder for +/- List (Grant Only) | This builder is responsible for building the objects to be used for the +/- list. Only the Grant .csv file will be completed under this task.
Builder for Graphs (Grant Only) | This builder is responsible fot building objects to be used for the graphs. Only the Grant .csv file will be used at this time.
Map Construction (Grant Only) | This task pertains to building a map of all Grant row objects.
Remaining Builder for +/- List | Same as previous builder for +/- list objects, except for the remaining three file types.
Remaing Builder for Row Objects | Same as for previous builder for graph objects, except for the remaing three file types.
Remaining Row Builders | Same as the row builder above, except implemented for the other three file types.
Remaining Error Checking | Same as the error checking above, except implemented for the other three file types.
Remaing Builders for Graphs | Same as previous builder for graphs, except expanded to include other file types.
Remaing Map Construction | Same as the map construction above, except implemented for the other three file types.
Main Window | Main window to display all elements of the program. (Including +/- List, graphs, date range filters, menu options etc.)
"+/-" Display List/Tree | Displays the currated information from the .csv in an expandable +/- list format.
Bar Graph | Displays data from the .csv as a function of time for a specific person.
Pie Graph | Displays a comparision of attributes of a specific person over time.
Graph Printing | Allows the user to print the data held in a graph.
Proper File Commenting | Ensuring the code is properly documentted.
Inspections and OO Metrics | Required for v2 submission.
Final Report | Required for v2 submission.
Green - Completed
Blue - Planned